## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	4
PROJECT NAME	IIIT Hiring Portal
PROJECT MENTOR	Raghu Reddy
TEAM MEMBERS	Abhishek Vinjamoori
	Sai Sahith Nama
	PVNS Chaitanya
	Kamalesh Tangudu
	Shantanu Prabhat

## Team Status
TEAM NAME	4
PROJECT NAME	IIIT Hiring Portal
PROJECT MENTOR	Raghu Reddy

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 16(nov 10-nov 16)
Client meet	Coordination	Abhishek	5	5	Done		0	0
making css pages	Development	Chaitanya	4	3	Done	coding the css elements of faculty pages	1	33.3333333333
making html pages	Development	Sahith	3	2	Done	coding the html elements of faculty pages	1	50
Django models,controls,raw-views	Development	Abhishek	7	8	Done	candidate notification page,faculty homepage	-1	12.5
Week 17(nov 17-nov 24)
making css for few pages	Development	Kamalesh	2	1.75	Ongoing	coding the css elements of hiring committee pages	0.25	14.2857142857
making html pages	Development	Sahith	2	1.5	Ongoing	coding the html elements of hiring committee pages	0.5	33.3333333333
Django models,controls,raw-views	Development	Abhishek	5	4	Ongoing	generation of one page summary,candidate review page,forwarding of appication	1	25
Preparation for R2	Documentation	Sahith	6	5	Ongoing	preparation of demo and presentation for R2	1	20
making css for the rest	Development	Chaitanya	2	1.75	Ongoing	coding the css elements for FAQ's,candidate review page.	0.25	14.2857142857

## Individual_Status
TEAM NAME	4
PROJECT NAME	IIIT Hiring Portal
PROJECT MENTOR	Raghu Reddy

Actvities	Abhishek Vinjamoori		Sai Sahith Nama		PVNS Chaitanya		Kamalesh Tangudu		Shantanu Prabhat		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 16(nov 10-nov 16)
Client meet	1	1	1	1	1	1	1	1	5	5
making css pages	0	0	0	0	2	1.5	2	1.5	0	0	4	3
making html pages	0	0	2	1.5	0	0	0	0	1	0.5	3	2
Django models,controls,raw-views	7	8	0	0	0	0	0	0	0	0	7	8
Week 17(nov 16-nov 24)
making css pages	0	0	0	0	1	1	1	0.75	0	0	2	1.75
making html pages	0	0	1	1	0	0	0	0	1	0.5	2	1.5
Django models,controls,raw-views	5	4	0	0	0	0	0	0	0	0	5	4
Preparing for R2	1	0.5	2	3	1	0.5	1	0.5	1	0.5	6	5

## 'file:///home/kamal/ssad-project-4/ssad_2015_team4/documents/StatusTracker.xls'#Instructions
TEAM NAME	4
PROJECT NAME	IIIT Hiring Portal
PROJECT MENTOR	Raghu Reddy
	Abhishek Vinjamoori
	Sai Sahith Nama
	PVNS Chaitanya
	Kamalesh Tangudu
	Shantanu Prabhat

## 'file:///home/kamal/ssad-project-4/ssad_2015_team4/documents/StatusTracker.xls'#Team_Status
Week 5 (August 31- sept 6)

Role preferences
Web framework setup
Develop questions for requirements elicitation
Get account and configure website
Research existing technology
Project synopsis writeup
Team Meeting
Status tracker
Week 6 (sept 7- sept 13)

Making client mockup pages
Web framework setup
Team Meeting

Week 8 (sept 14 - sept 20)

Prepare questions for next client meeting
Making the SRS document
Week 9(sept 21- sept 28)
Fixing client mockup pages
Continue with reverse process of application
Preparing the TestPlan document
Week 10(sept 29- oct 5)
Fixing reverse process
Learn Django
Preparing talk for R1
Preparing presentation for R1
Week 11(oct 6-oct 12)
Team Meeting
Preparing talk for R1

Week 12(oct 13-oct 19)
Prepare questions for next client meeting
Client meet
Changing the moqup pages

Week 13(oct 20-oct 26)
making css pages
making css pages
making html pages
making control structures
Week 14(oct 27-nov 2)

Week 15

Week 16

Week 17